## Sheet2
Local Network
Activity 1 - Run(Check) FNO to CCU Connectivity report |  | QA Validation Status | Error Description | Defect Severity |  |  | Assigned To
Check correct number of local ports as per design and build of the FNO (192 Port or 384 Port) | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
Total FNO cabinet local ports (X&Cpairs) in PNI that trace to CCU (CCB) aligns to the jumpering records and iPACT (LT Cards) | Internal |  |  | Major | Not Sampled |  | DSG | As-Built | Connectivity (Spatial)
CSS tie cable are spliced to the Pillar (CCU- CCB) | Internal |  |  | Major | Not Sampled |  | DSG | As-Built | Connectivity (Spatial)
CSS tie cable are spliced to the FTTN Cabinet (FNO) | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
Activity 2 - Boundary
Check ADA Boundary Attribute details Note: Boundary details must be blank, date fields should be blank ('none' is not acceptable). | Internal |  |  | Major | Not Sampled |  | RD completion | Civils | Design
House property boundary shown with house number and street name (visual check) incident to be raised | Internal |  |  | Minor | Not Sampled |  | LMS | Address management | Location Boundary
CSA ID to be checked and validated on the FSA boundary againt X-plans (to be updated in-house if missing) | Internal |  |  | Major | Not Sampled | amended in house | NDQ Desktop | As-Built | FSA boundary
Check all ADA Boundaries are created in the allocated SAM and check for overlapping | Internal |  |  | Major | Not Sampled |  | RD Completion | Civils | Design
Check Technology Type is set to Copper and Technology Subtype is set to FTTN |  |  |  | Major |  |  | RD Completion
Activity 3 - CCU/ Pillars
Correct number of CCU/Pillars located in correct location and has an address entered in spatial (confirm against Redline As built ) | Internal |  |  | Major | Not Sampled |  | NDQ As-built | As-Built | Site location (Spatial)
Check to see that Pillar is not missing in PNI |  |  |  | Major |  |  | DSG | As - Built | Connectiviy
Check the Pillar (CCU) reflects the correct SpatialNET Equipment (size and type) |  |  |  | Major |  |  | DSG | As - Built | connectivity
Check CSS tie cables are Jointed correctly to ( X&C pairs) inclusive of remediated work |  |  |  | Major |  |  | NDQ As built | As-built
Check the Pillar TLS ID is correct - cross referenced with Redline and JR (Telstra only) |  |  |  | Major | Not Sampled |  | NDQ As built | As-Built | Spatial Misalignment
Check the Pillar NBN Alternate Name (i.e. RELA:P21) NBN owned asset cross reference with Redline (Regions to investigate reasons behind mis-aligned New Pillar ID's) | Internal |  |  | Major | Not Sampled |  | NDQ As built | As-Built | Missing artefact (Spatial)
Activity 4 - Retrofit Pillars
Confirmation required for Correct Retro Fit Pillar Types under the variant (Rectangle, Standard) |  |  |  | Major |  |  | RD COMPLETION
Confirm correct size pillar to be loaded for Retro Fit Pillars |  |  |  | Major |  |  | RD COMPLETION
Check Retro fit Pillar has correct pillar type associated with the Attributes under the Variant (Rectangle, standard) |  |  |  | Major |  |  | DSG | Civils
Check CSS Tie cables are loaded correctly for retrofit pillars (Prysmian 400 pair Cu external grade cable (0.40) CPFUT/PE-CCU retrofit - diameter 28.7) |  |  |  | Major |  |  | As BUILT TEAM | Civils
Check that the 400pr cable does not exceed to pre-cut length of 50m (if this occurs please investigate if a joint has been installed and additional cables hauled) |  |  |  | Major |  |  | RD COMPLETION | Civils | Design
Check correct size pillar has been loaded for retro fit pillar (1800 type to ensure capacity of cross connect ports)) |  |  |  | Major |  |  | DSG
Activity 5 - Cables
CSS tie cable is annotated under each duct on its route (by turning on Layer 480) | Internal | Pass |  | Minor | Not Sampled |  | RD Completon | Civils | Design
CSS tie cable shown and correct size as per design and build and verify there is no duplication | Internal | Pass |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
CSS tie cable labelled correctly with the FSA, SAM, and ADA coding | Internal | Pass |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
CSS Tie cable attribute "Tie Cable:Y" for all cables (Tie cables only) | Internal | Pass |  | Major | Not Sampled |  | RD Completion | Civils | Design
Check CSS cables are attached to support structures |  |  |  | Major |  |  | NDQ As built | As-Built
CSS tie cables Original Pair Count, Gauge Diameter, Sheath Type, Core Construction Type |  |  |  | Major |  |  | RD Completion | Civils | Design
Activity 6 - Power Assets
RCD located in correct location as per Documents - Redline Markup and AC-SLD |  |  |  | Major |  |  | NDQ Asbuilt
FUS located in correct location as per Documents -Redline Markup and AC-SLD | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
FUS is attached to correct Pole or electrical pit as per Documents - Redline Markup and AC-SLD | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
PWC cable is annotated under each duct on its route (by turning on Layer 480), | Internal |  |  | Minor | Not Sampled |  | RD Completon | As-Built | Naming convention (Spatial)
PWC cable shown and correct size as per design and build and verify there is no duplication as per Redline Markup | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
PWC cable labelled correctly with the FSA, SAM, and ADA coding | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | Labelling | Cable
PWC cable attached to correct supports on its run | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
Power Pit size is correct as per documents - Redline Mark up and AC -SLD | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
Check all Power Equipment has been migrated to the correct PNI SpatialNET representation (As per Migrate RF Power Equipment function) | Internal |  |  | Major | Not Sampled |  | RD Completion | Civils | Design
Distribution Network
Activity 7 - Cables and Joints
DSS cable shown and correct size as per design and build (fibre count) as per redline Mark up plan/SLD | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
DSS cable labelled correctly with the FSA, SAM, ADA coding and verify there is no duplication | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
DSS cables attached to correct supports on their run and is not duplicated | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
DJLs shown in correct location and have address entered as per design and build, and is not duplicated | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
DJLs labelled correctly with the FSA,SAM, ADA coding and verify there is no duplication | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | Civils | Design
DJL splice reports show correct fibre connection | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
HSD cable shown and correct size as per Redline and SLD | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
HSD cable labelled correctly with the FSA, SAM, ADA coding and verify there is no duplication | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | Civils | Design
HSD cable attached to correct supports on its run | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
Run Mis-assigned Equipment report - identify local joints, and multiports not attached or away from its support | Internal |  |  | Major | Not Sampled |  | DSG | As-Built | Connectivity (Spatial)
Run Mis-assigned Equipment report - identify local joints, and multiports away from its support - visual checks |  |  |  | Minor |  |  | DSG | As-Built
Correct number of MPTs shown in correct locations and have an address entered as per design and build | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
MPTs labelled correctly with the FSA, SAM, ADA coding and verify there is no duplication | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
MPT splice reports show correct fibre connections | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
PIT sizes are correct as per design and build and Pit Remediation done in Spatial | Internal |  |  | Minor | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
Activity 8 - Physical Network Inventory - OSP
Run OSP report and verify asset capture has been loaded and is correct - for Constructed NBN owned infrastructure - Requirements include Owner (NBNco), Object status, Construction Actual date, Project name, Project number, As Built lengths, Cable batch numbers (CSS tie cable batch numbers are to be raised as a Minor - line 68) | Internal | Pass |  | Major | Not Sampled |  | NDQ Asbuilt | Civils | Missing artefact (Spatial)
Run OSP report and verify Asset Capture has been loaded and is correct for existing third party network - Original Network owner, Current Owner, object status | Internal | Pass |  | Major | Not Sampled |  | NDQ Asbuilt | Civils | Missing artefact (Spatial)
Verify batch numbers are provided and loaded into PNI for CSS tie cables |  | Manual | Manual | Minor |  |  | NDQ Asbuilt | Civils | Missing artefact (Spatial)
Check IWR numbers have been loaded in PNI and the OSP and sharepoint task are aligned |  | Manual | Manual | Major |  |  | NDQ Asbuilt
Note: Non-Blank for FTTx (TSS, DSS, HSD, HSL, LSS, MSS, C/X Pairs) - all required to be loaded in PNI for batch numbers
Note: Project name and Number not required for trenches
Section 2: Active
Activity 9 - Run FNO/CSD to FAN Connectivity report
Verify end to end connectivity from FNO to FAN. Confirm against active NDD E2E report, integration workbook, IL Workbook and path on SLD. Note - Manual trace from SFP (Tx) can be performed if automated report is not available | Internal |  |  | Major | Not Sampled |  | NDQ As built | As-Built | Reconciliation
Activity 10-Site Naming Convention
Check to see if Naming Convention for FNO in SpatialNET aligns with NDD | Internal |  |  | Major | Not Sampled |  | RD Completion | Civils | Design
Activity 11 -Site Details
Check Site Code, Node Name, Address and Object Status are loaded in PNI | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
FNO detailed drawing can be opened | Internal |  |  | Major | Not Sampled |  | RD Completion | Civils | Design
Logical name of each FNOs populated on each attribute- (in Export_asset_capture_report_for_site_combined) | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
Splitter installation - 384 type cabinet splitters required to be loaded in spatial which are physically installed in the field | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Naming convention (Spatial)
Splitter installation - Node jumpering template - splitters not physically installed but are required to total to 384 splitters which are required to be loaded in PNI | Internal |  |  | Minor | Not Sampled |  | NDQ Asbuilt | As-Built | Connectivity (Spatial)
Activity 12 -Spatial Subrack - FNO
Verify Rack details: Spatial-Rack Elevation View\Rack Details Inventory - against IPACT | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
Verify Subrack details: Spatial-Rack Elevation View\Rack Details - against IPACT | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
Verify Card details: Spatial-Rack Elevation View\Rack Details - against IPACT | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Missing artefact (Spatial)
Verify SFP details: Spatial-Rack Elevation View\Rack Details -against IPACT | Internal |  |  | Major | Not Sampled |  | NDQ Asbuilt | As-Built | Site location (Spatial)
Serial numbers - • Serial numbers displayed in iPACT (inclusive of Cabinet, Chasis Serial Number) align to the Integration Workbook | Internal |  |  | Major | Not Sampled |  | DP | Civils | Site location (Spatial)
Please check Batch numbers and Manufacturing dates for Batteries and are loaded in the Integration Workbook | Internal |  |  | Major |  |  | DP | Civils | Missing artefact (Spatial)
Verify FNO's have been integrated in iPACT (Note: Defect to be raised if FNO's are shown as Planned, Designed or Constructed) |  |  |  | Major |  |  | RD Completion
NOTE: ALL ISP Equipment to be loaded as "Constructed" only in PNI - check life cycle status on objects and ports (two reports -import/export) including termination Racks and Distribution Panels
NOTE: FNO's are integrated when shown in iPACT as - Integrated, FLS Supervised, NOC Supervised and In service. If shown as "Constructed" this means the FNO has yet to be integrated and is not to be confused with Object Status "constructed"
Activity 13-Spatial ODF port Allocation - FAN
Verify Port details at the FAN and check ODF port allocations are aligned to the Integration workbook and SLD |  |  |  | Major |  |  | NDQ As built | Active
Activity 14 -SPATIAL POWER
Check Pole ID's are loaded in PNI and are aligned to the AC SLD | Internal |  |  | Major | Not Sampled |  | DESG | As-Built
Perform visual check to ensure pole data is accurate |  |  |  | Minor |  |  | RD Completion
Activity 15- Equipment Specifications
Rack Location, Equipment Logical Name, Equipment Physical Name, Subrack Position (DSL/Kentrox Alarm Management, Eaton DC Distribution Module) | Internal |  |  | Major | Not Sampled |  | RD Completion | Civils | Design
Check correct Cabinet type has been installed - Alcatel Lucent/Nokia versus Commscope and confirm against iPACT and correct catalog ID |  |  |  | Major |  |  | DESG | As-Built | Design
Commscope Batteries - Check correct number of battery strings have been loaded (Note: 4 batteries if 4 cards or less installed and 8 batteries if 5 cards or more installed) |  |  |  | Major |  |  | NDQ Asbuilt | As-Built | Design
Activity 16- Alarm Management Patching
Verify connection between PDU and DSL | Internal | Failed | DSL Cable Not Traced | Major | Not Sampled |  | RD Completion | Civils | Design
Activity 17- ISP FNO - Physical Network Inventory
Run ISP report and verify asset capture has been loaded and is correct - for Constructed NBN owned infrastructure - Requirements include Owner (NBNco), Object status, Construction Actual date, Project name, Project number, Asbuilt lengths |  | Failed | EmptyValuespresent | Major |  |  | NDQ Asbuilt | Civils
Activity 18- DPBO configuration Profile
Confirm DPBO profile name has been loaded in iPACT against the DSLAM |  |  |  | Major |  |  | RD Completion
Note: 34db loss is equal to 40db loss and is acceptable
Section 3: Documents
SLD | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
As Built Red line | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
PNI Capture | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
Integration Workbook - ISAM integration details | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
AC SLD | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
Insertion Loss (IL) workbook | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
OTDR Trace Results | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
FTTN Jumpering Records | External |  |  | Major | Not Sampled |  | DP | Completion | Document Accuracy
iPact | Internal |  |  | Major | Not Sampled |  | iPact team | Completion | Site Access details
DPBO profiles (document can be found under Active NDD) | Internal |  |  | Major | Not Sampled |  | RD Completions | Completion | Reconciliation
NDQ Desktop raises defect if no DPBO document loaded into ConnectMTM. “Open” Defect sent to RD Design team.
1) RD Design team provides updated full ‘pillar-to-exchange’ trace report to Active Design Team. “Open” Defect sent to Active Design Team.
1) Active Design uploaded DPBO shapers into ConnectMTM. “Open” Defect sent to Integration team.
1) Integration team applies DPBO shapers to DSLAMs. Defect set to “Resolved” and sent to NDQ Desktop.
NDQ Desktop confirms DPBO shapers loaded to DSLAM. Defect set to “Closed